## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29
Select/DeselectAll Button | 1 | 0 | 0 | 0 | 0
Filter the course that meets all the requirement | 1.5 | 1 | 0 | 0 | 0
Put all the information in the corresponding table column | 3 | 1 | 0 | 0 | 0
Place the checkbox in the column | 1 | 1 | 0 | 0 | 0
Set up the Listener mode for the checkbox | 0 | 1 | 3 | 0 | 0
Display the consoler information | 0 | 0 | 2.5 | 0 | 0
Debugging based on message on piazza | 1 | 1 | 1 | 1 | 2
Write Comments | 0 | 0 | 2.5 | 1.5 | 1
Unit Test | 0 | 0 | 0 | 3 | 3
Total hours | 7.5 | 5 | 9 | 5.5 | 6