## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29
Write Subject Scraper | 3 | 2 | 1 | 0.5 | 0
Modify Class "Controller" | 2 | 1 | 0 | 0 | 0
New Class "CourseSFQ" | 1 | 1 | 0.5 | 0 | 0
New Class "SectionSFQ" | 1 | 2 | 0.5 | 0 | 0
New Class "Instructor" | 0 | 3 | 1 | 0 | 0
Write SFQ Scraper | 0 | 0 | 2.5 | 0 | 0
Debug | 0 | 1 | 3 | 3 | 2
Write Comments | 0 | 0 | 2.5 | 1.5 | 1
Unit Test | 0 | 0 | 0 | 4 | 2
Total hours | 7 | 10 | 11 | 9 | 5