## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29
Course Scraper | 1 | 3 | 1.5 | 0.5 | 0
Modify Class "Course" | 1 | 1 | 0 | 0 | 0
New Class "Section" | 3 | 1 | 0 | 0 | 0
Modify Class "Slot" | 1 | 1 | 0 | 0 | 0
Backend Information | 0 | 1 | 0 | 0 | 0
Timetable update | 0 | 0 | 2.5 | 0 | 0
Random Color Module | 0 | 0 | 2 | 0 | 0
Write Comments | 0 | 0 | 2.5 | 1.5 | 1
Unit Test | 0 | 0 | 0 | 3 | 3
Total hours | 6 | 7 | 8.5 | 5 | 4